## Sheet1
2014-0186 | Nicole Victoria | Software Engineering |  | Casa de Muebles File System
Risk | Category | Probability | Impact | RMMM
Client does not understand or know fully the project requirements | Customer | 80% | 2 | Present sample or similar projects by the development team (if existing) to client to explain what project requirements are
Not all members of the development team have experience working on a similar project | Staff Size and Experience | 80% | 3 | Assign experienced developers as team leaders, or pair off inexperienced developers with experienced ones who will mentor them
Client might not be familiar with (and might have questions about) the software engineering process | Customer | 80% | 3 | Set aside a meeting to explain to client how the software engineering process goes. Use diagrams, case studies, videos, if necessary
The developers have complaints about compensation and work load/hours expected of them | Staff Size and Experience | 70% | 1 | Developer contracts must clearly state the agreed upon compensation and work hours they must render for this project.
The client might purchase hardware or software incompatible with the system | Environment and Technology Risks | 70% | 1 | Inform client what hardware or software the company must provide their employees
Revisions requested by the client are too many to handle (after delivery) | Product size | 70% | 1 | Specify in the contract the scope and duration of the development project. Stipulate the scope of revisions you will accept, and the changes to timeline the revision will entail.
Development cost accrues due to errors in the system | Business Impact | 70% | 1 | Plan an adequate amount of testing and debugging time; make sure to confirm with client (and get feedback from client) if their requirements are met during the design and planning phase
Client is not trained enough to operate the software/to get most out of the software and reverts to traditional methods of production | Customer | 70% | 1 | Orient the client during user acceptance phase on how to use the software and refer to the documentation
Not all members of the development team are familiar with the software process model to be used in the project | Process definition | 70% | 2 | Orient the development team how you'll go about the process; prepare a clear GANTT chart so everyone can visualize how long each phase would take, when to expect certain milestones, and how much output is expected at different points in the timeline
Documentation is not adequate nor clear enough | Business Impact | 70% | 2 | Train developers and their team leaders to do proper documentation by specifying the correct documentation format; provide a template, if necessary
Coding inconsistency among developers/development teams | Process definition | 70% | 2 | Meet with developers and agree on a code style to be used in the project
Client might complain about the cost of developing the system | Business Impact | 70% | 2 | Give a well-written quotation document to the client, i.e. specify the standard company rates, provide them with a clear project timeline, give a projection on how the software will make their production easier and, in the long run, more efficient and cheaper
The skill level/skill set of the developers may widely vary | Staff Size and Experience | 70% | 3 | Assign experienced developers as team leaders or on critical tasks, or pair off inexperienced developers with experienced ones who will mentor them
Scope of software is too large for specified project duration | Product size | 60% | 1 | Design the software into small, manageable modules, and set ample time for the integration phase. Schedule frequent milestones in project timetable
Project might not be delivered to client on time due to scope | Business Impact | 60% | 1 | Use an appropriate software process model (e.g. phased-release model) to maximize the time (be able to code modules simultaneously) and ensure delivery of certain (if not all) modules
End users may be unused to the shift to a file system to manage their tasks | Business Impact | 60% | 1 | Take time to train the end users on how to use the program; design the GUI as simple as possible; provide them with software documentation
Developers/development use different tools | Environment and Technology Risks | 60% | 2 | Make sure tools used by the developers are the same; if cost is an issue, look for open-source tools
Client location is too far away; immersion will entail higher expenses | Business Impact | 60% | 4 | Include the travel expenses in the quotation; plan the trip and hire a vehicle so the developers are not inconvenienced by the long commute
Developers assigned to the module of a certain department might not understand how that department operates | Business Impact | 50% | 1 | Make sure the developers stick to their assigned departments in all phases of software engineering; if shifting can't be helped, ask shiftee developer to relay the documented information (gathered during immersion) to replacement developer
Client complains about the project duration/timeline | Business Impact | 50% | 2 | Specify clearly in the contract the project duration; never overpromise; give ample time for testing; make sure everyone meets their milestones (client included)
New design patterns and algorithms might be needed in the project | Environment and Technology Risks | 50% | 3 | Meet with team heads and discuss whether these new design patterns and algorithms need to be implemented in this project. If no, set another time for developers to study and implement these; if yes, make sure developers have the proper documentation/references
Huge number of users logged in may make the system slow | Business Impact | 40% | 1 | Include in the documentation this possibility; include this in client training lecture
Not all members are familiar with software testing tools and/or application security measures | Process definition | 40% | 2 | Take time during the early leg of the development process to familiarize developers with the testing tools and app security measures that will be used
Team might not understand where to start (on) or what information to gather during the immersion activity | Business Impact | 40% | 3 | Orient team on what information to gather, what they need to observe and look out for during the immersion activity. Provide them a questionnaire, form, or checklist to make information gathering easier on their end
Client may have apprehensions about the immersion process | Customer | 40% | 3 | Orient client before hand what would happen during the immersion activity. Schedule visits to department in such a way that each department will not be bothered too much during peak hours of work. Seek out suggestions from the client on how to make the immersion process easier; ask them if they can assign a manager or supervisor to oversee the visit and entertain questions from the developers/researchers
Not all developers assigned to the project are committed to the entire duration of the project | Staff Size and Experience | 30% | 2 | Verify every developer's schedule and make appropriate changes to timeline/role assignment; assign committed developers to more critical tasks
New tools/framework/API might be needed in the project | Environment and Technology Risks | 30% | 2 | Meet with team heads and discuss whether these new tools/framework/API need to be implemented. If no, set another time for developers to study and implement these new tools; if yes, make sure developers have the proper documentation/references to help them use the new framework/tools/API
There might be PWDs or people from the client company with special needs who will use the software, and the software might not be accessible to them | Environment and Technology Risks | 30% | 3 | Inquire company about PWDs and people with special needs in initial requirement gathering phase; during immersion, document how they do their jobs